Upskill Energy — Project Plan & Budget (Grant Application Framework)

Aligned to the Access → Transition → Advance → Empower Model

1️⃣ Project Overview

Project Title:
“Upskill Energy Academy — Building the Workforce for the Energy Transition”

Project Duration:
24 months (divided into three phases)

Lead Organisation:
Upskill Energy Ltd.

Delivery Partners:

- East of England Energy Group (EEEGR)

- Regional FE College Network (Norfolk, Suffolk, Humber)

- Local Authorities & LSIP Skills Partnerships

- Employer Partners (Vattenfall, EDF, ScottishPower Renewables, Centrica)

- Technology Partner (Digital LMS & Credentialing Platform Provider)

Project Aim:
To create an integrated energy workforce development ecosystem that enables new entrants, skilled trades, and existing professionals to access, transition, and advance within the energy sector — supported by an innovative digital learning and assurance platform.

2️⃣ Project Objectives

| Objective | Outcome |
| --- | --- |
| 1. Develop Access Pathways | Create and deliver 3 foundation “Access to Energy Trades” programs (Electrical, Mechanical, Instrumentation) with embedded HSE and employability units. |
| 2. Deliver Transition Programs | Build 5 cross-industry transition modules (Hydrogen, Offshore Wind, Solar & Storage, Automation, Carbon Capture). |
| 3. Advance Workforce Capability | Design 6 bespoke CPD and site-specific training packages for employers focusing on operational performance and compliance. |
| 4. Deploy Digital Learning Platform | Implement LMS and analytics dashboard to host, credential, and report learning outcomes. |
| 5. Workforce Impact & Inclusion | Train at least 1,500 learners with 85% employment or upskilling outcomes, prioritising local residents and underrepresented groups. |
| 6. Create Sustainable Funding Model | Combine funded delivery, employer co-investment, and digital licensing to ensure long-term sustainability beyond the grant. |

3️⃣ Project Phases

Phase 1 — Design & Infrastructure (Months 1–6)

- Curriculum mapping for Access, Transition, and Advance frameworks.

- Platform build and integration (LMS, analytics, digital credentialing).

- Partnership mobilisation (EEEGR, colleges, employers, funders).

- Quality assurance framework and trainer accreditation.

Deliverables:

- 10 accredited course frameworks ready for pilot.

- LMS live with credentialing engine.

- Signed partnership agreements with FE and employers.

Phase 2 — Pilot & Delivery (Months 7–18)

- Deliver pilot Access & Transition programs through FE partners.

- Deploy first CPD packages for employer sites.

- Measure outcomes, gather feedback, refine content.

- Employer co-funding activated via Transition and CPD contracts.

Deliverables:

- 800 learners trained (60% new entrants / 40% upskillers).

- 25+ employers engaged.

- 80% job placement or internal progression.

Phase 3 — Expansion & Sustainability (Months 19–24)

- Launch licensing model to regional partners.

- Deliver advanced site packages to new employer contracts.

- Publish regional workforce impact report.

- Secure follow-on funding and reinvest in digital R&D.

Deliverables:

- 1,500 total learners trained.

- 100% digital delivery readiness for national replication.

- Demonstrable 5:1 social ROI and net-zero workforce impact report.

4️⃣ Detailed Budget (Indicative)

| Category | Description | Cost (£) | Funding Source |
| --- | --- | --- | --- |
| Curriculum & Framework Development | Design, accreditation, SME consultants, and materials for Access, Transition, and CPD programs | £100,000 | LSIF / Innovate UK |
| Digital Platform Development | LMS build, analytics integration, cloud hosting, credentialing engine | £150,000 | Innovate UK / Match Funding |
| Trainer & QA Network | Recruitment, training, audit systems, and delivery QA | £75,000 | LSIF / Employer Co-funding |
| Employer Engagement & Industry Partnerships | EEEGR partnership coordination, advisory panels, site integration | £25,000 | LSIF / Employer In-kind |
| Marketing & Recruitment | Learner outreach, branding, events, media | £40,000 | LSIF / Employer Co-funding |
| Delivery Costs (FE Partners) | Facility hire, consumables, assessment, insurance | £50,000 | LSIF / FE Match |
| Inclusion & Community Programs | Targeted outreach for local residents, youth, displaced workers | £30,000 | LSIF / Local Authority |
| Evaluation & Impact Reporting | External evaluation, social value reporting, ROI metrics | £15,000 | LSIF |
| Project Management & Administration | Oversight, finance, reporting, governance | £15,000 | LSIF |
| Contingency (5%) | Reserve for unforeseen expenses | £25,000 | Mixed |
| Total Project Budget |  | £525,000 | LSIF / Innovate UK / Employer Match |

Co-Funding Contribution Goal:
60% public grant funding (£315K LSIF / £150K Innovate UK)
40% private and in-kind match funding (£60K employer / £50K FE / £50K Upskill reinvestment)

5️⃣ Key Performance Indicators (KPIs)

| KPI | Target | Measurement Method |
| --- | --- | --- |
| Learners Enrolled | 1,500 total | LMS enrolment data |
| Learner-to-Employment Rate | ≥ 85% | Employer feedback & learner tracking |
| Employer Partnerships | 25+ active | Signed agreements |
| Training Modules Developed | 14 total | QA certification records |
| Social ROI | ≥ 5:1 | External impact analysis |
| Platform Uptime | ≥ 99.5% | System analytics |
| Partner Satisfaction | ≥ 90% | Quarterly surveys |

6️⃣ Project Governance & Delivery Team

| Role | Responsibility |
| --- | --- |
| Project Director (Upskill Energy) | Overall leadership, finance, stakeholder liaison |
| Programme Manager | Day-to-day project coordination and reporting |
| Curriculum Development Lead | Framework design, quality assurance |
| Digital Product Manager | LMS build and integration oversight |
| EEEGR Liaison | Industry engagement and employer coordination |
| Evaluation Partner (External) | Independent impact measurement |
| Finance Manager (Part-time) | Budget control, audit, compliance |

7️⃣ Sustainability & Legacy Plan

After the grant-funded phase:

- Programs become self-funding through AEB, Bootcamp, and employer CPD revenue.

- Platform transitions to a subscription and licensing model for colleges and OEM academies.

- Consultancy division scales through retained employer partnerships.

- IP, content, and technology continue to generate revenue without dependence on grant funding.

Outcome:
By Month 24, Upskill Energy achieves commercial sustainability, trains over 1,500 people, and establishes a replicable model for UK-wide rollout.

8️⃣ Strategic Fit Summary

| Funding Body | How the Project Aligns |
| --- | --- |
| LSIF (Local Skills Improvement Fund) | Builds regional skills pipelines in priority sector (energy & green technologies) through employer-college partnerships. |
| Innovate UK | Demonstrates innovation through digital learning and workforce analytics technology. |
| Local Authorities & LSIPs | Delivers measurable local employment outcomes and social mobility impacts. |
| Employer Partners | Provides co-funding and real-world validation of workforce demand. |

9️⃣ Funding Readiness Checklist

✅ Detailed budget prepared and justified
✅ Delivery partners identified
✅ Letters of support ready from FE and employers
✅ Risk and evaluation framework established
✅ Social impact model quantified
✅ Financial sustainability plan post-grant